## Slide 1: ROADMAP DEVELOPMENT
Introduction

## Slide 2: Roadmap development
Illustration of the tool
Summarise key activities required in terms of technologies, capabilities, culture, ecosystem and finance based on your earlier assessments to the ‘List of activities’ sheet.
Write key functions contributing to the implementation of your circular idea to the ‘Responsibilities and timing’ sheet
Define a timeline for your transformation journey
Define responsible functions (and if possible, name people to approach) and appropriate phase for each activity
Tip: Use sticky notes to list the activities – it saves time and allows flexibility!
INTRODUCTION
Purpose
Instructions
The purpose of the roadmap development tool is to support you in planning the first steps on your circular transformation journey on a high-level, through listing key activities, estimating the time to complete them and prioritising them into short, medium and long-term.
Supporting materials
Chapter 5:
How to design the transformation journey?
Illustrative playbook pages – please refer to the entire chapter for support.
Three phases of the transformation journey
Key barriers and ways to overcome them

## Slide 3: Roadmap development
Example
EXAMPLE
II. Attract & Win
III. Scale fast & keep growing
Develop processes and partnerships and pilot new solution to convey benefits
Adopt multiple circular business models across own operations and value chain
__________
__________
Time
Function 2:
Sourcing & Procurement
Function 3:
Manufacturing
Function 4:
Marketing & Sales
Function 5:
Leadership
Function 1:
Design + R&D
Roadmap development – Responsibilities and timing
Define your time line– depending on the pace you chose
I. Explore & Shape
Develop concepts for target business models, look for partners, design and test prototype(s)
6 months
12 months
Screen and assess new material suppliers
Design and test prototype with customers in workshops
Develop circular design criteria and guide
Select pilot product(s)
Assess required changes in production
Develop pricing models for new modular offering
Promote pilot offering
Approve launch of pilot
Secure funding: contact bank to get credit
Implement required changes in production
Develop final product concept based on customer input
Prepare pilot launch activities
Organise training on modular product sales
Monitor pilot results and decide on next steps
Hire new staff
Prepare scale up of production
Collect and map customer needs & pain points (input from sales)
Scale modular design for other product categories
Participate in sales training on modular product sales
Start designing service concept for new product
Finalise and validate service concept with customers
Develop final service concept based on customer input
Establish supplier agreements
Engage with supplier to trigger changes
Implement continuous supplier scoring and engagement
Implement required changes in production
Develop pricing models for new modular offerings
Launch new modular product categories
Develop pricing models for new service offerings
Promote new modular offerings
Prepare service launch activities
Promote new service offering
Reassess suppliers
Launch service concept
Organise training on service sales
Participate in training on service sales
Hire new staff for service sales
Screen and assess potential technology providers
Screen technology partners for service concept
Communicate transformation kick-off and define targets and incentives
Change supplier base/ deselect supplier as required
Perform supplier assessment
Illustrative example for Build to last business model with consecutive development of Repair & Maintain

## Slide 4: ROADMAP DEVELOPMENT
Tool

## Slide 5
Roadmap development – List of activities (1/2)
Capabilities
Technologies
Culture
List key activities with estimate of required time (think about short- and long-term)

## Slide 6
Roadmap development – List of activities (2/2)
Finance
Ecosystem
List key activities with estimate of required time (think about short- and long-term)

## Slide 7
Roadmap development – Responsibilities and timing
II. Attract & Win
III. Scale fast & keep growing
Develop processes and partnerships and pilot new solution to convey benefits
Adopt multiple circular business models across own operations and value chain
__________
__________
Time
Function 2:
Function 3:
Function 4:
Function 5:
Function 1:
Define your timeline– depending on the pace you choose
I. Explore & Shape
Develop concepts for target business models, look for partners, design and test prototype(s)